## Sheet1
|  | Apr-2019 | May-2019 | Jun-2019 | Jul-2019 | Aug-2019 | Sep-2019 | Oct-2019 | Nov-2019 | Dec-2019 | Jan-2020 | Feb-2020 | Mar-2020 | Apr-2020
AI for City Planning | 1 | May Yong (0.5) | May Yong (0.5)
| 2 | Louise Bowler (0.5) | Louise Bowler (0.5)
AIDA-Lloyds | 1 | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | RESOURCE REQUIRED (0.5) | RESOURCE REQUIRED (0.5) | RESOURCE REQUIRED (0.5) | RESOURCE REQUIRED (0.5) | RESOURCE REQUIRED (0.5)
| 2 | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5)
Bayesian Performance Tuning | 1 | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5)
Biobank algorithm | 1 | Miguel Morin (0.6) | Miguel Morin (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6)
| 2 | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6)
CWTS - Leiden | 1 | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2)
Clean Air | 1 | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.4)
DS for Sustainable Development | 1 | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5)
Fitbit classification | 1 | Miguel Morin (0.5) | Miguel Morin (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5)
| 2 | Evelina Gabasova (0.5) | Evelina Gabasova (0.5)
GUARD | 1 | Jim Madge (0.5)
Knowledge Flows | 1 | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5)
Leeds: Lomax, Malleson, Heppenstall | 1 | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6)
| 2 | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6)
Living With Machines | 1 | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0)
| 2 | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5)
| 3 | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1)
| 4 | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1)
NATS | 1 | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5)
| 2 | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5)
| 3 | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5)
Nocell | 1 | Oliver Strickson (0.6) | Oliver Strickson (0.6)
| 2 | James Geddes (0.5) | James Geddes (0.5)
Parallel Monte Carlo | 1 | Miguel Morin (0.5) | Miguel Morin (0.5)
Streaming healthcare analytics | 1 | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5)
Team management | 1 | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1)
Uncertainty in Government Modelling | 1 | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6)
Urban observatory spatial sampling | 1 | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5)