## Sheet1
|  | Nov-2018 | Dec-2018 | Jan-2019 | Feb-2019 | Mar-2019 | Apr-2019 | May-2019 | Jun-2019 | Jul-2019 | Aug-2019 | Sep-2019 | Oct-2019 | Nov-2019 | Dec-2019 | Jan-2020 | Feb-2020 | Mar-2020 | Apr-2020 | May-2020 | Jun-2020 | Jul-2020 | Aug-2020 | Sep-2020 | Oct-2020 | Nov-2020 | Dec-2020 | Jan-2021 | Feb-2021 | Mar-2021
AI for City Planning | 1st | May Yong (0.5) | May Yong (0.5) | May Yong (0.5) | May Yong (0.5) | May Yong (0.5) | May Yong (0.5) | May Yong (0.5)
| 2nd | Louise Bowler (0.5) | Louise Bowler (0.5) | Louise Bowler (0.5) | Louise Bowler (0.5) | Louise Bowler (0.5) | Louise Bowler (0.5) | Louise Bowler (0.5)
AIDA | 1st | Camila Rangel Smith (1.0) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5)
| 2nd | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5)
| 3rd | May Yong (0.5) | May Yong (0.5) | May Yong (0.5) | May Yong (0.5) | May Yong (0.5)
| 4th | Giovanni Colavizza (0.5) | James Geddes (0.2) | James Geddes (0.2) | James Geddes (0.2) | James Geddes (0.2)
AIDA-Lloyds | 1st | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5)
| 2nd |  |  | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5)
ALOGIT Python | 1st |  | Jim Madge (0.4) | Jim Madge (0.5) | Jim Madge (0.5) | Jim Madge (0.5)
BA (IAG) | 1st | Radka Jersakova (1.0) | Radka Jersakova (1.0) | Radka Jersakova (0.5)
| 2nd | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | James Geddes (0.2)
| 3rd | James Geddes (0.2) | James Geddes (0.2)
Bayesian Performance Tuning | 1st |  |  |  | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5)
Biobank algorithm | 1st | Miguel Morin (0.6) | Miguel Morin (0.6) | Miguel Morin (0.6) | Miguel Morin (0.6) | Miguel Morin (0.6) | Miguel Morin (0.6) | Miguel Morin (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6)
| 2nd |  |  | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6) | Evelina Gabasova (0.6)
CWTS - Leiden | 1st |  |  | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2)
Clean Air | 1st | [5 empty] | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.4)
Crypto Federated Learning (SHEEP) | 1st | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5)
| 2nd | Nick Barlow (0.5) | Nick Barlow (0.5)
| 3rd | Oliver Strickson (0.2) | Oliver Strickson (0.2)
DS for Sustainable Development | 1st |  |  | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5)
| 2nd |  |  | RESOURCE REQUIRED (0.0)
Data Science Benchmarking | 1st |  | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5) | Tomas Lazauskas (0.5)
DetectorChecker | 1st | Tomas Lazauskas (0.5) |  | Tomas Lazauskas (0.5)
Fitbit classification | 1st | Miguel Morin (0.1) | Miguel Morin (0.5) | Miguel Morin (0.5) | Miguel Morin (0.5) | Miguel Morin (0.5) | Miguel Morin (0.5) | Miguel Morin (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5)
| 2nd |  |  | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5)
GUARD | 1st |  | Jim Madge (0.4) | Jim Madge (0.5) | Jim Madge (0.5) | Jim Madge (0.5) | Jim Madge (0.5)
| 2nd |  | Giovanni Colavizza (0.4) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2) | Giovanni Colavizza (0.2)
Knowledge Flows | 1st |  | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5) | Camila Rangel Smith (0.5)
Leeds: Lomax, Malleson, Heppenstall | 1st | [5 empty] | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | RESOURCE REQUIRED (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6)
| 2nd | [5 empty] | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6) | Louise Bowler (0.6)
Living With Machines | 1st | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0) | David Beavan (1.0)
| 2nd | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5)
| 3rd | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | Giovanni Colavizza (0.5) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1)
| 4th |  | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1)
Maru | 1st | Oliver Strickson (0.5) | Oliver Strickson (0.6) | Oliver Strickson (0.6) | Oliver Strickson (0.6) | Oliver Strickson (0.6)
Misinformation | 1st | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5)
| 2nd | Martin O'Reilly (0.5) | Martin O'Reilly (0.0) | Martin O'Reilly (0.3)
NATS | 1st | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Kasra Hosseini (1.2) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5) | Timothy Hobson (0.5)
| 2nd | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Radka Jersakova (0.5) | Timothy Hobson (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5) | Radka Jersakova (0.5)
| 3rd |  |  |  | Evelina Gabasova (0.5) | Radka Jersakova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5) | Evelina Gabasova (0.5)
| 4th |  |  |  | Kasra Hosseini (0.5) | Evelina Gabasova (0.5)
Nocell | 1st | James Geddes (0.5) | James Geddes (0.5) | Oliver Strickson (0.6) | Oliver Strickson (0.6) | Oliver Strickson (0.6) | Oliver Strickson (0.6) | Oliver Strickson (0.6)
| 2nd |  |  | James Geddes (0.5) | James Geddes (0.5) | James Geddes (0.5) | James Geddes (0.5) | James Geddes (0.5)
Parallel Monte Carlo | 1st | Miguel Morin (0.1) | Miguel Morin (0.5) | Miguel Morin (0.5) | Miguel Morin (0.5) | Miguel Morin (0.5) | Miguel Morin (0.5) | Miguel Morin (0.5)
| 2nd |  |  | James Robinson (0.1) | James Robinson (0.2)
Probabilistic FEM | 1st |  | Eric Daub (0.5) | Eric Daub (0.5) | Eric Daub (0.5) | Eric Daub (0.5)
SPF Learning Machines | 1st |  |  | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1)
SPF TPS Theme Management | 1st | James Hetherington (0.6) | James Hetherington (0.6) | James Hetherington (0.6) | James Hetherington (0.6) | James Hetherington (0.6)
Safe Haven | 1st | James Robinson (0.5) | Martin O'Reilly (0.8) | James Robinson (0.4) | James Robinson (0.3) | James Robinson (0.5)
| 2nd |  | James Robinson (0.5) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1)
| 3rd |  | James Hetherington (0.1)
Sargasso (Intel Sparse) | 1st | Oliver Strickson (0.5) | Oliver Strickson (0.5)
Streaming healthcare analytics | 1st | [5 empty] | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5) | James Robinson (0.5)
Team management | 1st | Martin O'Reilly (0.5) | Martin O'Reilly (0.0) | Martin O'Reilly (0.7) | Martin O'Reilly (1.0) | Martin O'Reilly (1.0) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1)
| 2nd |  |  | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1)
The Turing Way | 1st | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5) | Sarah Gibson (0.5)
| 2nd | Louise Bowler (0.5) | Louise Bowler (0.5) | Louise Bowler (0.5) | Louise Bowler (0.5) | Louise Bowler (0.5)
Training delivery | 1st | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1) | James Hetherington (0.1)
UQM^3 | 1st |  |  | Eric Daub (0.4) | Eric Daub (0.5) | Eric Daub (0.5)
Uncertainty in Government Modelling | 1st | [5 empty] | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6) | Camila Rangel Smith (0.6)
Urban observatory spatial sampling | 1st | [5 empty] | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5) | Nick Barlow (0.5)