## Sheet1
|  | Nov-2018 | Dec-2018 | Jan-2019 | Feb-2019 | Mar-2019 | Apr-2019 | May-2019 | Jun-2019 | Jul-2019 | Aug-2019 | Sep-2019 | Oct-2019 | Nov-2019 | Dec-2019 | Jan-2020 | Feb-2020 | Mar-2020 | Apr-2020 | May-2020 | Jun-2020 | Jul-2020 | Aug-2020 | Sep-2020 | Oct-2020 | Nov-2020 | Dec-2020 | Jan-2021 | Feb-2021 | Mar-2021
Camila Rangel Smith | 1st | AIDA (0.8) | Knowledge Flows (0.4) | Knowledge Flows (0.4) | Knowledge Flows (0.4) | Knowledge Flows (0.4) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5) | Uncertainty in Government Modelling (0.5)
| 2nd |  | AIDA (0.4) | AIDA (0.4) | AIDA (0.4) | AIDA (0.4) | Knowledge Flows (0.4) | Knowledge Flows (0.4) | Knowledge Flows (0.4) | Knowledge Flows (0.4) | Knowledge Flows (0.4) | Knowledge Flows (0.4) | Knowledge Flows (0.4) | Knowledge Flows (0.4)
David Beavan | 1st | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8) | Living With Machines (0.8)
Eric Daub | 1st |  | Probabilistic FEM (0.4) | Probabilistic FEM (0.4) | UQM^3 (0.4) | UQM^3 (0.4)
| 2nd |  |  | UQM^3 (0.3) | Probabilistic FEM (0.4) | Probabilistic FEM (0.4)
Evelina Gabasova | 1st | NATS (0.4) | NATS (0.4) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5)
| 2nd | BA (IAG) (0.4) | BA (IAG) (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4)
| 3rd |  |  | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4)
Giovanni Colavizza | 1st | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4)
| 2nd | AIDA (0.4) | GUARD (0.3) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2) | CWTS - Leiden (0.2)
| 3rd |  | AIDA (0.1) | GUARD (0.2) | GUARD (0.2) | GUARD (0.2)
James Geddes | 1st | Nocell (0.4) | Nocell (0.4) | Nocell (0.4) | Nocell (0.4) | Nocell (0.4) | Nocell (0.4) | Nocell (0.4)
| 2nd | BA (IAG) (0.2) | BA (IAG) (0.2) | BA (IAG) (0.2) | NATS (0.2) | NATS (0.2)
| 3rd | AIDA (0.2) | AIDA (0.2) | AIDA (0.2) | AIDA (0.2) | AIDA (0.2)
James Hetherington | 1st | SPF TPS Theme Management (0.5) | SPF TPS Theme Management (0.5) | SPF TPS Theme Management (0.5) | SPF TPS Theme Management (0.5) | SPF TPS Theme Management (0.5) | Team management (0.1) | Team management (0.1) | Team management (0.1) | Team management (0.1) | Team management (0.1) | Team management (0.1) | Team management (0.1) | Team management (0.1) | Team management (0.1) | Living With Machines (0.1) | Living With Machines (0.1) | Living With Machines (0.1)
| 2nd | Training delivery (0.1) | Training delivery (0.1) | SPF Learning Machines (0.1) | SPF Learning Machines (0.1) | Team management (0.1) | Living With Machines (0.1) | Living With Machines (0.1) | Living With Machines (0.1) | Living With Machines (0.1) | Living With Machines (0.1) | Living With Machines (0.1) | Living With Machines (0.1) | Living With Machines (0.1) | Living With Machines (0.1)
| 3rd |  | Living With Machines (0.1) / Safe Haven (0.1) | Team management (0.1) / Safe Haven (0.1) / Living With Machines (0.1) / Training delivery (0.1) | Team management (0.1) / Safe Haven (0.1) / Living With Machines (0.1) / Training delivery (0.1) | Living With Machines (0.1) / SPF Learning Machines (0.1) / Safe Haven (0.1) / Training delivery (0.1)
James Robinson | 1st | Safe Haven (0.4) | Safe Haven (0.4) | Misinformation (0.4) | Misinformation (0.4) | Safe Haven (0.4) | Clean Air (0.4) | Clean Air (0.4) | Clean Air (0.4) | Clean Air (0.4) | Clean Air (0.4) | Clean Air (0.4) | Clean Air (0.4) | Clean Air (0.4) | Streaming healthcare analytics (0.4)
| 2nd | Misinformation (0.4) | Misinformation (0.4) | Safe Haven (0.3) | Safe Haven (0.3) | Misinformation (0.4) | Streaming healthcare analytics (0.4) | Streaming healthcare analytics (0.4) | Streaming healthcare analytics (0.4) | Streaming healthcare analytics (0.4) | Streaming healthcare analytics (0.4) | Streaming healthcare analytics (0.4) | Streaming healthcare analytics (0.4) | Streaming healthcare analytics (0.4) | Clean Air (0.3)
| 3rd |  |  | Parallel Monte Carlo (0.1) | Parallel Monte Carlo (0.1)
Jim Madge | 1st |  | ALOGIT Python (0.3) | ALOGIT Python (0.4) | ALOGIT Python (0.4) | ALOGIT Python (0.4) | GUARD (0.4)
| 2nd |  | GUARD (0.3) | GUARD (0.4) | GUARD (0.4) | GUARD (0.4)
Kasra Hosseini | 1st |  |  |  | NATS (0.4) | NATS (1.0)
Louise Bowler | 1st | The Turing Way (0.4) | The Turing Way (0.4) | The Turing Way (0.4) | The Turing Way (0.4) | The Turing Way (0.4) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5) | Leeds: Lomax, Malleson, Heppenstall (0.5)
| 2nd | AI for City Planning (0.4) | AI for City Planning (0.4) | AI for City Planning (0.4) | AI for City Planning (0.4) | AI for City Planning (0.4) | AI for City Planning (0.4) | AI for City Planning (0.4)
Martin O'Reilly | 1st | Team management (0.4) | Safe Haven (0.7) | Team management (0.5) | Team management (0.8) | Team management (0.8)
| 2nd | Misinformation (0.4) | Team management (0.0) | Misinformation (0.3)
| 3rd |  | Misinformation (0.0)
May Yong | 1st | AI for City Planning (0.4) | AI for City Planning (0.4) | AI for City Planning (0.4) | AI for City Planning (0.4) | AI for City Planning (0.4) | AI for City Planning (0.4) | AI for City Planning (0.4)
| 2nd | AIDA (0.4) | AIDA (0.4) | AIDA (0.4) | AIDA (0.4) | AIDA (0.4)
Miguel Morin | 1st | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5) | Biobank algorithm (0.5)
| 2nd | Parallel Monte Carlo (0.1) | Parallel Monte Carlo (0.4) | Parallel Monte Carlo (0.4) | Parallel Monte Carlo (0.4) | Parallel Monte Carlo (0.4) | Parallel Monte Carlo (0.4) | Parallel Monte Carlo (0.4)
| 3rd | Fitbit classification (0.1) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4) | Fitbit classification (0.4)
Nick Barlow | 1st | Crypto Federated Learning (SHEEP) (0.4) | Crypto Federated Learning (SHEEP) (0.4) | DS for Sustainable Development (0.4) | DS for Sustainable Development (0.4) | DS for Sustainable Development (0.4) | Urban observatory spatial sampling (0.4) | Urban observatory spatial sampling (0.4) | Urban observatory spatial sampling (0.4) | Urban observatory spatial sampling (0.4) | Urban observatory spatial sampling (0.4) | Urban observatory spatial sampling (0.4) | Urban observatory spatial sampling (0.4) | Urban observatory spatial sampling (0.4) | Urban observatory spatial sampling (0.4)
| 2nd | AIDA (0.4) | AIDA (0.4) | AIDA (0.4) | AIDA (0.4) | AIDA (0.4) | DS for Sustainable Development (0.4) | DS for Sustainable Development (0.4) | DS for Sustainable Development (0.4) | DS for Sustainable Development (0.4) | DS for Sustainable Development (0.4) | DS for Sustainable Development (0.4) | DS for Sustainable Development (0.4) | DS for Sustainable Development (0.4) | DS for Sustainable Development (0.4)
Oliver Strickson | 1st | Maru (0.4) | Maru (0.5) | Nocell (0.5) | Nocell (0.5) | Nocell (0.5) | Nocell (0.5) | Nocell (0.5)
| 2nd | Sargasso (Intel Sparse) (0.4) | Sargasso (Intel Sparse) (0.4) | Maru (0.5) | Maru (0.5) | Maru (0.5)
| 3rd | Crypto Federated Learning (SHEEP) (0.2) | Crypto Federated Learning (SHEEP) (0.2)
Radka Jersakova | 1st | BA (IAG) (0.8) | BA (IAG) (0.8) | AIDA-Lloyds (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4)
| 2nd |  |  | BA (IAG) (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4)
Sarah Gibson | 1st | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4) | AIDA-Lloyds (0.4)
| 2nd | The Turing Way (0.4) | The Turing Way (0.4) | The Turing Way (0.4) | The Turing Way (0.4) | The Turing Way (0.4)
Timothy Hobson | 1st | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | NATS (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4)
| 2nd | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4) | Living With Machines (0.4)
Tomas Lazauskas | 1st | Crypto Federated Learning (SHEEP) (0.4) | Data Science Benchmarking (0.4) | Data Science Benchmarking (0.4) | Bayesian Performance Tuning (0.4) | Bayesian Performance Tuning (0.4) | Bayesian Performance Tuning (0.4) | Bayesian Performance Tuning (0.4) | Bayesian Performance Tuning (0.4) | Bayesian Performance Tuning (0.4) | Bayesian Performance Tuning (0.4) | Bayesian Performance Tuning (0.4) | Bayesian Performance Tuning (0.4) | Bayesian Performance Tuning (0.4)
| 2nd | DetectorChecker (0.4) | Crypto Federated Learning (SHEEP) (0.4) | DetectorChecker (0.4) | Data Science Benchmarking (0.4) | Data Science Benchmarking (0.4)